## Feuille1
Priority	Steps by priority	Example site	Structure exemple site	Beta site	Final web site	Status

Steps

10	LOGIN USER DATA BASE
	Login with mandatory email to be able to advise people when vote will be available			http://beta.referenduminternational.org/index.php?title=Sp%C3%A9cial:Connexion&type=signup&returnto=Accueil	http://fr.wiki.referenduminternational.org/index.php?title=Sp%C3%A9cial:Connexion&type=signup&returnto=Accueil
	Put live online after beta testing

20	QUESTIONS DATA BASE
	Data base of questions and answer to be ask to know what kind of democraty population want so, we will know what to do next for development.
	Posting the question on the internet to be voted on present web site or directly on the wiki base.	http://internationalreferendum.org/index.php		http://beta.referenduminternational.org/index.php?title=Qui_doit_d%C3%A9cider_des_normes_internationales%3F
	First question to post: "Who has to decide international norms?"
	login required to vote but not to see the question and answer
	Put live online after beta testing

	Result visible to all in real time for each question
	Put live online after beta testing

	User data account have to be very secure
	Vote page and results data base have to be very secure
	Put live online after beta testing

	Intégration of data base and vote page to wiki base if not done.
	Everything that could be damage by wiki security upgrade have to be noted to be test first on beta web site before updating final web site.
	For security and reduce data base hacking everything that we will do and data base need to be on referenduminternational.org web site				http://referenduminternational.org/
	wiki base will be install on www.wiki.internationalreferendum.org				http://wiki.internationalreferendum.org
	Put live online after beta testing

25	QUESTION STATUS DATA BASE
	Question and choice of answers with proposer name
	Seconder name after first vote
	5 status possible:
	1- Proposition
	2- Under vote
	3- Adopted
	4- Rejected
	5- Merge with similar question

30	MULTILINGUAGE WEB SITES
	First page in every language web site	http://www.wikipedia.org/		http://structure.referenduminternational.org/index.php	http://referenduminternational.org/
					http://internationalreferndum.org/
					etc.

	Web sites in English, French, Japanese and other volunteers language
	Put live online after beta testing

	Wiki base auto-detect user system or browser software and show page in user langage or we have to install wiki base in every-language?
	Put live online after beta testing

	Index wiki base page have to be lock. Only administrator for every language could change it.	http://en.wikipedia.org/wiki/Main_Page			http://en.wiki.referenduminternational.org/
	Index wiki page will be setup in volunteers language. English, French and Japanese for the moment.	http://fr.wikipedia.org/wiki/Wikip%C3%A9dia:Accueil_principal	To be done in wiki: http://fr.structure.referenduminternational.org/index.php		http://fr.wiki.referenduminternational.org/
		http://ja.wikipedia.org/wiki/%E3%83%A1%E3%82%A4%E3%83%B3%E3%83%9A%E3%83%BC%E3%82%B8			http://jp.wiki.referenduminternational.org/
	Put live online after beta testing

100	MULTILINGUAL DATA BASE
	Questions and answers in every language have to be link to the same result data base	http://referenduminternational.org/		http://beta.referenduminternational.org/index.php?title=Qui_doit_d%C3%A9cider_des_normes_internationales%3F	http://fr.wiki.referenduminternational.org/index.php?title=Qui_doit_d%C3%A9cider_des_normes_internationales%3F
	Put live online after beta testing

	Question and choice of answers have to be lock and visible on every language page into the original posting language			http://beta.referenduminternational.org/index.php?title=Qui_doit_d%C3%A9cider_des_normes_internationales%3F_%28please_translate_in_English%29	http://fr.wiki.referenduminternational.org/index.php?title=Qui_doit_d%C3%A9cider_des_normes_internationales%3F_%28please_translate_in_English%30
	Put live online after beta testing

	Questions and choice of answers could be change only by the original writer.
	Put live online after beta testing

	Any one login user could add other answers to be choose for existing question
	Put live online after beta testing

	Any one login could vote and write a translation on the different language page
	Any one login could correct the translation but cannot change the original language question.
	Put live online after beta testing

	For security the choice of answers have to be with numbers so translation have to correspond to the original choices in original language to void inversion of answers into the data base
	Put live online after beta testing

1000	TRANSLATION REQUEST
	After translation, page title is change for the translated language for every language page translated			http://beta.referenduminternational.org/index.php?title=Who_have_to_decide_the_internationals_norms%3F	http://en.wiki.referenduminternational.org/index.php?title=Who_have_to_decide_the_internationals_norms%3F
	Put live online after beta testing

	Automaticaly after posting a question. Question and answer are visible 2 times. 1 fix in original language and 1 in original language with link "Please translate"
	Log in people could translate without modificating codes linking question, answers and answers number to the data base.
	Put live online after beta testing

2000	2 DISCUSSION PAGES
	Change de "discussion" page name for "question discussion"
	Add one more discussion page named "translation discussion"
	Put live online after beta testing

3000	DONATIONS
	Adding donation page with links	http://referenduminternational.org/Dons.php			http://beta.referenduminternational.org/index.php?title=Don
	Page cannot be modified by other than administrators
	Put a link to the donation page into the left navigation menu			http://referenduminternational.org/Dons.php
	Put live online after beta testing

10000	ALL LANGUAGE SETUP
	Setup of 371 available language web site
	Setup of automatic original language question in every language page.
	Setup of translation access to every body login.
	Put live online after beta testing

20000	SEARCH MENU
	Setup page by status question
	Setup page with list of categories questions (see next page for the list)
	Setup page with sub-categories questions (see here for the list)
	Put live online after beta testing

	Setup drop down menu by status question on index page left navigation window
	Setup drop down menu by categories questions (see next page for the list) on index page left navigation window
	Setup drop down menu by sub-categories questions (see here for the list) on index page left navigation window
	Put live online after beta testing

100000	SOCIAL NETWORK PROMOTION
	Development of social network application to publish individual voting results on main social network: twitter, Facebook, etc.
	-Publishing user: Question. Answer, (With referendum user name and) on www.internationalreferendum.org
	Add setup option in user account to link their account to the applications: Twitter, Facebook, etc.
	Add three voting publishing button: 1- Vote and publish on my social network, 2- vote and ask before publishing and 3- vote (only, not publish on my social network)

200000	CATEGORIE VOTE
	People could vote to change question categories if mispalce
	People could vote to change question sub-categories if mispalce

300000	QUESTION FUSION
	People could vote for question fusion if 2 questions are too similar

400000	PUBLIC QUESTION POSTING
	People could post question with answer in categories
	People could post amendment with answers

500000	PUBLIC ANSWER POSTING
	People could add new answers options
	People could vote to reject an answer if not appropriate

600000	AMENDMENT
	Amendment questions to be link to questions
	People could add amendment question

	CATEGORIES	SUB-CATEGORIES
	EMERGENCY	Exemple: Irak, USA, Afghanistan, Soudan, natural cataclysm
	FOUNDER NORMS
	CONSTITUTIVE NORMS
	CHARTER OF DUTY, RIGHTS AND FREEDOM
	CULTURALS NORMS
	ECONOMICAL NORMS	Public expense
		International building construction code norms
		Advertising norms
		Public health norms/ Ecology
		Polution norms
		International labor norms

	POLITICAL NORMS	Civil code norms
		Criminal code norms
		Penal norms
		Regional political norms